## ProductBacklog
PRODUCT BACKLOG
|  |  | Batch 2018_2019 | Free Time Shopping
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
SB1 | US1 | Admin | Managing all the sign's up done by the user | Admin have a record of all the sign's up done by the user
SB2 | US2 | Admin | Managing all the login's done by the user | Admin have a record of all the login's done by the user
SB3 | US3 | Admin | Manages the database for the logined users | Admin can manage the data
SB4 | US4 | Admin | Manage the forget password option for the users | Admin can manage the forget password option
SB5 | US5 | Admin | Sends a confirmation mail when a user sign's up | Admin can send a confirmation mail when any user sign's up
SB6 | US6 | Admin | Won't let a user to login until he confirms the signed up login id | Admin will check for that the user has confirmed the email id or not
SB7 | US7 | Admin | Check the number users online on the website | Admin can check the number users online
SB8 | US8 | Admin | Check the number of hits on the website | Admin can check the number of hits
SB9 | US9 | Admin | Manage the password options | Admin can manage password options
SB10 | US10 | Admin | Manage the inventory panel for the website | Admin can manage the inventory panel for the website
SB11 | US11 | Admin | Add new items in the inventory database | Admin can add new items in the inventory database
SB12 | US12 | Admin | Delete the unused or unpopular items from the database | Admin can delete the unused or unpopular items
SB13 | US13 | Admin | Manage the discounts given on each items | Admin can manage the discounts given
SB14 | US14 | Admin | Check if there are more than one active seession of a user | Admin can check if there are more than one active seession of a user
SB15 | US15 | Admin | Delete the suspicious accounts | Admin can delete any suspicious account
SB16 | US16 | Admin | Delete accounts of users who post false information | Admin can delete accounts of users who post false information
SB17 | US17 | Admin | Delete the accouts of users who post nudity | Admin can delete the accouts of users if anything is imprompt
SB18 | US18 | Admin | Check the profit generated each month | Admin can check the profit generated each month
SB19 | US19 | Admin | Stocking of new items on the website | Admin can stock new items
SB20 | US20 | Admin | Deletion of the items which will not be available anymore | Admin can delete the items which will not be available anymore
SB21 | US21 | Admin | Managing all the filters for shopping on the website | Admin can manage all the filters for shopping
SB22 | US22 | Admin | Manage the sorting option for shopping | Admin can manage the sorting option for shopping
SB23 | US23 | Admin | Manage each users shopping cart | Admin can manage each users shopping cart
SB24 | US24 | Admin | Address of each user should be auto read whenever placing a new order | Address of each user can be auto read
SB25 | US25 | Admin | Sending OTP for the payment gateway for netbanking and card payments | Admin can send otp for the payment gateway for netbanking
SB26 | US26 | Admin | Cash on Delivery option will be managed according to the users need | Admin can manage the cash on delivery option
SB27 | US27 | Admin | The product needs to be managed which a user wants to sell | Admin can manage the products which the users are selling
SB28 | US28 | Admin | All the details should be proper when a user is selling any product | Admin should check that all the information added by the user against the product is correct
SB29 | US29 | Admin | All the comments will be coming to the Admin panel | Admin should check all the comments added by the users
SB30 | US30 | Admin | All the queries asked by the users needs to be managed by the Admin | Admin can check and manage all the queries
SB31 | US31 | Admin | All the queries needs to be answered through the Admin Panel | Admin needs to answer all the queries
SB32 | US32 | Admin | All the answers to the queries will reach the user through email | Admin should answer the query of any user through email
SB33 | US33 | Admin | Can check and edit anything in the comments section | Admin can check and edit any comment
SB34 | US34 | Admin | Can manage the interface given for the users | Admin can manage the interface of the website
SB35 | US35 | Admin | Can delete any item from the website | Admin can delete any item from the website
SB36 | US36 | Admin | Can add any item on the website | Admin can add any item on the website
SB37 | US37 | Admin | Can make edit the description for the website | Admin can make edit the description of the website
SB38 | US38 | Admin | Contact section will be managed by the Admin Panel | Admin can manage the contact sectionon the website
SB39 | US39 | Admin | Can add new developers which are helping the Admin team | Admin can add new developers
SB40 | US40 | Admin | Meet the team panel needs to be managed by the Admin | Admin can manage meet the team panel on the website
SB41 | US41 | Admin | Security of the website | Admin can control the security of the website
SB42 | US42 | Admin | Supports the forget password option | Admin can support the forget password option
SB43 | US43 | Admin | Cares for the site | Admin can take care of the website
SB44 | US44 | Admin | Provides a wishlist option to all the users | Admin can provide a wishlist option to the users
SB45 | US45 | Admin | Provides an option to add innumerable things in the wishlist | Admin can provide an option to add innumerable things in the wishlist
SB46 | US46 | Admin | Can remove any item from any users wishlist which is out of stock | Admin can remove any item from any users wishlist which is put of stock
SB47 | US47 | Admin | Need to take care that the website does not get hacked by anyone | Admin needs to take care that the website does not get hacked
SB48 | US48 | Admin | Needs to check that the user is getting the order in the delivery dates | Admin needs to check that the user is getting the order in the delivery dates
SB49 | US49 | Admin | Needs to figure the problem if the user is not receiving the order in time | Admin needs to figure the problem if the user is not receiving the order in time
SB50 | US50 | Admin | Can update the prices of any item | Admin can update the prices of any items
SB51 | US51 | User | Can Sign Up if new to the website | User can sign up if new on the website
SB52 | US52 | User | Should provide with the correct personal information to sign up | User should provide with the correct personal information
SB53 | US53 | User | Should confirm the email ID from the confirmation email sent | User should confirm the email id through the confirmation mail
SB54 | US54 | User | Now the new user can check all the items present on the website | User can check all the items present on the website
SB55 | US55 | User | Can login if is a existing user | User can login if is an existing user
SB56 | US56 | User | Can check all the items present on the website | User can check all the items present on the website
SB57 | US57 | User | Can Purchase any item from the website | User can purchase any item from the website
SB58 | US58 | User | Can sell any item on the website | User can sell any item on the website
SB59 | US59 | User | Users can comment on all the items which they have/not purchased from the website | User can comment on all the items which they have/not purchased
SB60 | US60 | User | Users can buy innumerable items from the website | User can buy innumerable items from the website
SB61 | US61 | User | Users can sell innumerable items on the website | User can sell innumerable items on the website
SB62 | US62 | User | Users can save many items on the website in the wishlist | User can save many items on the website in the wishlist panel
SB63 | US63 | User | Users can give feedback for the website | User can give feedback for the website
SB64 | US64 | User | Users can ask put any query in the Query section | User can ask put any query in the query section
SB65 | US65 | User | Users will get the answers to their queries through email | User will get the answers to their queries through email
SB66 | US66 | User | Users need to provide all the information about the item they need to sell | User need to provide all the information about the item they need to sell
SB67 | US67 | User | Users can buy all the items present on the website | User can buy all the items present on the website
SB68 | US68 | User | Users will have the benefits of all the discounts availing on the website | User will have the benefits of all the discounts availing on the website
SB69 | US69 | User | Users will have the benefit of the wishlist option | User will have the benefit of the wishlist option
SB70 | US70 | User | FAQ will help the users to get answers to there questions easily | User will get the answers to their queries through FAQ section easily
SB71 | US71 | User | Users can ask questions in the FAQ sections | User can ask questions in FAQ section as well
SB72 | US72 | User | Users can buy any item from the website | User can buy any item from the website
SB73 | US73 | User | Users can do the payment for the order according to their wish | User can do the payment for the order according to their wish
SB74 | US74 | User | Users can choose pay on delivery option | User can choose pay on delivery option for any product
SB75 | US75 | User | Users can choose net banking payment gateway | User can choose net banking payment gateway
SB76 | US76 | User | Users can choose card payment gateway | User can choose card payment gateway to do the payments
SB77 | US77 | User | Users can exchange the purchased product | User can exchange the purchased product
SB78 | US78 | User | Users can return the purchased product | User can return the purchased product
SB79 | US79 | User | To get the refund, users need to provide their account details | User get the refund, but for that users need to provide their account details
SB80 | US80 | User | To exchange users can buy any piece from the same product | User can exchange can but another piece from the same product
SB81 | US81 | User | If a user forgets the password for their account they can change it | User can change the password if they forget the password
SB82 | US82 | User | Security question will help the user to change their password with this option | User can reset the password with the help of the security question
SB83 | US83 | User | User can check all the options related to product | User can check all the options realted to the product
SB84 | US84 | User | User can filter the options to buy according to their wish | User can filter the options to buy according to their wish
SB85 | US85 | User | User can cancel the order according to their wish | User can cancel the order the order according to their wish
SB86 | US86 | User | User uploads a item which they want to sell needs to be shipped by the user only | User uploads a item which they want to sell needs to be shipped by the user only
SB87 | US87 | User | User can use the contact us option to ask for any query | User can use the contact us option to ask for any query
SB88 | US88 | User | User can upload their profile picture | User can upload their profile picture
SB89 | US89 | User | User can change their personal information | User can change their personal information
SB90 | US90 | User | User can change their mobile number | User can change their mobile number
SB91 | US91 | User | User can add multiple address | User can add multiple address
SB92 | US92 | User | User can check their order history | User can check their order history
SB93 | US93 | User | User ask as many questions as they want | User ask as many questions as they want
SB94 | US94 | User | If the user is selling any product and the buyer does not like the product the user need to get back the order | User have to take back the product if not product selled by the user
SB95 | US95 | User | User can delete their account from the admin panel | User can delete their account
SB96 | US96 | User | Users can not check any others account | User cannot check any others account
SB97 | US97 | User | Users can not delete their comment once done | User can not delete their comment once done
SB98 | US98 | User | Users can not delete their question once asked in FAQ section | User can not delete their question once asked in FAQ section
SB99 | US99 | User | User can check the about option in the website | User can check the about option on the website
SB100 | US100 | User | User can check the meet the team option | User can check the meet the team option on the website

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 |  | SB1/D1/T1
SB1/D1/T2
SB1/D1/T3
SB1/D1/T4
SB1/D1/T5
SB1/D1/T6
SB1/US2 |  | SB1/D2/T1
SB1/D2/T2
SB1/D2/T3
SB1/D2/T4
SB1/D2/T5
SB1/US3 |  | SB1/D3/T1
SB1/D3/T2
SB1/D3/T3
SB1/D3/T4
SB1/US6 |  | SB1/D4/T1
SB1/D4/T2
SB1/D4/T3
SB1/D4/T4
SB1/D4/T5
SB1/US7 |  | SB1/D5/T1
SB1/D5/T2
SB1/D5/T3
SB1/D5/T4
SB1/US27 |  | SB1/D6/T1
SB1/D6/T2
SB1/D6/T3
SB1/D6/T4
SB1/D6/T5
SB1/US27 |  | SB1/D7/T2
SB1/D7/T3
SB1/D7/T4
SB1/D7/T5
SB1/US150 |  | SB1/D8/T1
SB1/D8/T2
SB1/D8/T3
SB1/D8/T4
SB1/US28 |  | SB1/D9/T1
SB1/D9/T2
SB1/D9/T3
SB1/D9/T4
SB1/D9/T5
SB1/US50 |  | SB1/D10/T1
SB1/D10/T2
SB1/D10/T3
SB1/D10/T4
SB1/D10/T5
SB1/US53 |  | SB1/D11/T2
SB1/D11/T3
SB1/D11/T4
SB1/D11/T5
SB1/US55 |  | SB1/D12/T1
SB1/D12/T2
SB1/D12/T3
SB1/D12/T4
SB1/US51 |  | SB1/D13/T1
SB1/D13/T2
SB1/D13/T3
SB1/D13/T4
SB1/D13/T5
SB1/US70 |  | SB1/D14/T1
SB1/D14/T2
SB1/D14/T3
SB1/D14/T4
SB1/D14/T5
SB1/US71 |  | SB1/D15/T2
SB1/D15/T3
SB1/D15/T4
SB1/D15/T5
SB1/US72 |  | SB1/D16/T1
SB1/D16/T2
SB1/D16/T3
SB1/D16/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 120
2018-09-11 | 80 | 100
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 0 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
| Add Department | SB2/D1/T1 | Designing the GUI | SP
|  | SB2/D1/T2 | Connection with database to fetch the data | RA
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TA into the application(using poornima email account) | SB2/D2/T1 | Designing of GUI | PB
|  | SB2/D2/T2 | Validating user input at client level | RM
|  | SB2/D2/T3 | Validating user input at server level | SP
|  | SB2/D2/T4 | Connection with Database to insert the record. | RA
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TA Receiving Confirmation Email | SB2/D3/T1 | Designing of Email(to be send) | PB
|  | SB2/D3/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D3/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TO into the application(using poornima email account) | SB2/D4/T1 | Designing of GUI | PB
|  | SB2/D4/T2 | Validating user input at client level | RM
|  | SB2/D4/T3 | Validating user input at server level | SP
|  | SB2/D4/T4 | Connection with Database to insert the record. | RA
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TO Receiving Confirmation Email | SB2/D5/T1 | Designing of Email(to be send) | PB
|  | SB2/D5/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D5/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D5/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Add Subject | SB2/D6/T1 | Designing of GUI | PB
|  | SB2/D6/T2 | Validating user input at client level | RM
|  | SB2/D6/T3 | Validating user input at server level | SP
|  | SB2/D6/T4 | Connection with Database to insert the record. | RA
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register Timetable Co-ordinator into the application | SB2/D7/T1 | Designing of GUI | PB
|  | SB2/D7/T2 | Validating user input at client level | RM
|  | SB2/D7/T3 | Validating user input at server level | SP
|  | SB2/D7/T4 | Connection with Database to insert the record. | RA
|  | SB2/D7/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Timetable Co-ordinator Receiving Confirmation Email | SB2/D8/T1 | Designing of Email(to be send) | PB
|  | SB2/D8/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D8/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days